## plan
Sportifry
Group06 - 19CLC9
Project Start Date: | 2021-10-13 |  |  |  |  | October | [20 empty] | November | [29 empty] | December | [29 empty] | January
 | time axis 2021-10-13 to 2022-01-09
Milestone description | Assigned to | Progress | Start | Days | Expectation | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Sprint 1
Software Development Plan | All members | 90% | 16/10/2021 | 21 | Complete | bar: F to T
Vision document | Tri, Nhan, Phat | 90% | 16/10/2021 | 21 | Complete 1,2,3,4.2,4.3 | bar: F to T
Sprint 2
Design database structure | Phat, Huy | 50% | 29/10/2021 | 5 | Efficient data storage | bar: F to F
Revised Software Development Plan | Tri, Phat | 100% | 30/10/2021 | 7 | Resolve all errors | bar: F to F
Revise Vision Document | Tri, Phat, Trung | 100% | 30/10/2021 | 7 | Resolve all errors | bar: F to F
Use-case specification | All members | 90% | 2021-06-11 | 8 | Detailed specification | bar: F to F
Use-case model | All members | 90% | 29/10/2021 | 7 | Detailed model | bar: F to F
Sprint 3
Specify Software Architecture | All members | 90% | 19/11/2021 | 7 | Detailed software architecture | bar: S to F
Revise Use-case model | Tri, Phat | 100% | 13/11/2021 | 6 | resolve all errors | bar: S to F
Revise use-case specification | Tri, Trung, Phat | 100% | 13/11/2021 | 6 | resolve all errors | bar: S to F
Construct class diagram | All members | 100% | 2021-12-11 | 6 | organized and feasible class structure | bar: S to F
Collecting sample data for the application | Tri, Trung, Phat | 60% | 2021-12-11 | 14 | relevant data | bar: S to F
Sprint 4
Modify software architecture | All members | 100% | 26/11/2021 | 3 | resolve all errors | bar: S to F
Sketch the ui prototype | Tri, Phat, Trung | 100% | 26/11/2021 | 14 | ui sketch meets the requirements of user interface designing criteria | bar: S to F
Implement login and first layout | Nhan, Huy | 100% | 26/11/2021 | 14 | efficient features' implementation | bar: S to F
Collecting sample data | All members | 100% | 26/11/2021 | 14 | relevant data | bar: S to F
Sprint 5
Implement music site | Huy | 100% | 2021-11-12 | 7 | Complete implementation | bar: S to F
Implement todo site | Nhan | 85% | 2021-11-12 | 7 | Complete implementation | bar: S to F
Implement navigation | Huy, Nhan | 100% | 2021-11-12 | 7 | Complete implementation | bar: S to F
Conducting tests using automated testing | All members | 100% | 18/12/2021 | 7 | Large coverage test cases, as many defects detected as possible | bar: S to F
Report test results and handle defects | All members | 100% | 18/12/2021 | 7 | Suitable solution for errors and bugs detected | bar: S to F
Sprint 6
Modify all documents | All members | 100% | 25/12/2021 | 7 | Complete documents | bar: S to T
Resolve all detected errors and bugs | All members | 100% | 25/12/2021 | 7 | Complete implementation | bar: S to T
Prepare for product release and presentation | All members | 100% | 25/12/2021 | 14 | bar: S to T